## Task List
Week # | Task # | Task Description | Estimated Time (Hours) | Complete? (Y/N) | Total Hours | 106
3 | 1 | Create the template task list. | 0.5 | Y
3 | 2 | Choose research question | 1 | Y
3 | 3 | Scope project and define computational tool approach | 2 | Y
3 | 4 | Review assignment requirements, rubric, and deliverables | 1 | Y
3 | 5 | Identify core cognitive science concepts for framing | 3 | Y
4 | 6 | Start rough literature review for LLM memory management | 5 | Y
4 | 7 | Review papers on cognitive science memory methods | 5.5 | Y
4 | 8 | Start citation list | 3 | Y
4 | 9 | Rough draft of project pitch | 2 | Y
4 | 10 | Review and finalize project pitch | 1 | Y
PROJECT PITCH DUE
5 | 11 | Finalize research question, hypotheses, and evaluation plan | 3 | Y
5 | 12 | Select benchmark and dataset | 4 | Y
6 | 13 | Setup colab, huggingface, and notebook skeleton | 4.5 | Y
6 | 14 | Implement basic LLM with chat history | 3 | Y
6 | 15 | Run and debug initial baseline tests | 4 | Y
7 | 16 | Design gist / frame representation schema | 3 | Y
7 | 17 | Implement initial gist-memory extraction pipeline | 6.5 | Y
8 | 18 | Implement question answering from extracted frames | 5.5 | Y
OPTIONAL MIDPOINT CHECK-IN DUE
9 | 19 | Debugging generation, JSON parsing, and answer formatting | 5 | Y
9 | 20 | Refactoring notebook and code | 4 | Y
9 | 21 | Adding semantic evaluation pass and plotting of results | 1 | Y
9 | 22 | Run subset experiments and reviewing error cases | 1 | Y
9 | 23 | Comparison of outputs | 1 | Y
10 | 24 | Initial rough draft and finishing literature review | 5 | Y
10 | 25 | Simplify architecture to two-pass evaluation method | 2.5 | Y
11 | 26 | Revise rough draft until results | 4 | Y
11 | 27 | Final bug fixes for code | 3 | Y
12 | 28 | Writing discussion, conclusion, limitations | 4 | Y
12 | 29 | Add bibliography and abstract | 1 | Y
13 | 30 | Preparing appendices | 1 | Y
13 | 31 | Final rewrites and proof reading | 9 | Y
FINAL REPORT DUE
14 | 32 | Draft presentation outline | 1 | N
14 | 33 | Create slides | 3 | N
14 | 34 | Practice presenting | 1 | N
14 | 35 | Record presentation | 2 | N
FINAL PRESENTATION DUE
Note on A1: The week of the semester, from week 3 to week 16.
Note on B1: An identifer for each task. This is used for easier conversation, e.g. "It looks like you didn't finish Task 5."
Note on C1: A brief (~1 sentence or fragment) description of the task.
Note on D1: The estimated number of hours to complete the task.